## Sheet1
| ROHIT | NISHANT | SASWATA | CHANGES
WEEK-1 | CREATE TABLES | LOGIN PAGE | SIGN UP FORM
WEEK-2 | ADD FUNCTIONALITY OF SIGN UP AND LOGIN
WEEK-3 | DATA ENTRY INTO DB | TOPIC SELECTION |  | demo defects week-2
WEEK-4 | TEST PAGE FRONT END AND ADD RESTRICTIONS
WEEK-5 | PROFILE DETAILS BACKEND | VIEW PROFILE DETAILS
WEEK-6 | ADMIN BACKEND | ADMIN VIEW
WEEK-7 | TESTING OF PROJECT USING SELENIUM
WEEK-8 | BUFFER FOR IMPLEMENTING NECESSARY CHANGES
WEEK-9 | PROJECT REPORT AND FINAL DEMO